## Sheet1
Sr. No. | Task | Assigned to | Complete By | Status | Notes
1 | Create Github Repo | Jason | 2017-10-24 | Incomplete | Need Mugdha's Github ID
2 | Gather Images | Jason | 2017-10-26 | Completed
3 | Gather Images | Ling | 2017-10-26 | In Progress
4 | Gather Images | Mugdha | 2017-10-26 | In Progress
5 | Design and provide Interfaces for each module | Jason, Ling, Mugdha | 2017-10-31 | Incomplete
6 | Build Image Loader Input: Directory with subdirectories labelled as good & bad Output: LookUpTable built by using image feature extractor | Mugdha | 2017-11-04 | Incomplete
7 | Build Image Feature Extractor 1. Input for feature extractor should be an image file 2. Output should be a feature vector | Ling | 2017-11-06 | Incomplete
8 | Learn about Latex | Jason | 2017-11-04 | Incomplete
9 | Build interface to Scikit learn classifiers to convert image feature vectors into a format acceptable to the scikit learn classifiers Input: LookUpTable, Test Dataset | Jason | 2017-11-04 | Incomplete
10 | Build Distance Computation Function to be used in algorithms such as KNN, K-Means etc 1. Input: 2 Image Feature Vectors 2. Distance between the two vectors | Ling | 2017-11-06 | Incomplete
11 | Integration and Bug Fixes | TBD | 2017-11-07 | Incomplete
12 | Complete Report | TBD | 2017-11-08 | Incomplete
13 | Build UI that allows users to upload their images | TBD | TBD | Incomplete
14 | Build UI that will present images to user to classify them as good or bad | TBD | TBD | Incomplete | While this is a 'good to have', the Prof. sounded really excited about this and we should try as much as possible to incorporate this into our project
15 | Build Pipeline to retrieve user images and likes from Facebook | TBD | TBD | Incomplete
16 | Figure out a way to replace user specified 'good' or 'bad' by Social Media parameters | TBD | TBD | Incomplete
17 | Figure out transforms to convert bad images to good ones | TBD | TBD | Incomplete
18 | Figure out perfromance to compute the effectiveness of the enhancer | TBD | TBD | Incomplete
19 | Build functionality to calculate performance metric of enhancer | TBD | TBD | Incomplete